## progress
date | area | details | status
2024-11-01 | scaffold | Initialized TyreVisionX repo structure and configs | done
2024-11-01 | tooling | Added Makefile, requirements, CI workflow | done
2024-11-01 | pipeline | Implemented data loaders, transforms, training/eval/export | done
2024-11-01 | inference | Created FastAPI service, Streamlit app, demo scripts | done
2024-11-01 | testing | Added pytest smoke tests for transforms/datasets/metrics/service | done
2024-11-30 | data | Imported Tyre dataset into data/D1_tyrenet and generated manifests/splits | done